## Product Backlog
| Fysieke component |  | Digitale component
Onderdeel | Prioriteit | Onderdeel | Prioriteit | Prioriteit:
Bord lay-out |  | Digital dices |  | High
Bord Foundation |  | Digitale gebeurtenissen |  | Medium
Bord Design |  | Path tracking (1) |  | Low
Bord Decoratie |  | Rule checking (2)
Gebeurtenissen |  | Digitale bank
Kaarten Dynamiek |  | Digitale graanvoorraad
Kaarten Design |  | GUI
Dobbelstenen |  | spelers invoeren
Pionnen |  | scherm met beurt info
Boten |  | mini overzicht spelers
Fiches |  | Boot data
Geld |  | Custom events
Obstakels concept |  | Thema
Obstakels productie
Spelregelboekje
Opbergdoos
Struikrover
Extra bord elementen

## Sprint 1 Backlog
Onderdeel | Moscow | Prioriteit | Status | Opmerkingen | Assignees
Bord lay-out | Must |  |  | Een houten bord lijkt de voorkeur te hebben, houdt hier rekening mee in de lay-out. | Ariano
Gebeurtenissen | Must |  |  | Eerste lijst met gebeurtenissen in txt bestand op drive, na balancen speldynamiek kaarten maken. | Alexander
Kaarten Dynamiek | Must |  |  | Gebeurtenissen kunnen eenvoudig getest worden met het event.py script dat op de drive staat. | Alexander
Dobbelstenen | Must |  |  |  | Avesh
Pionnen | Must |  |  | Tijdelijk, zo goedkoop mogelijk. | Avesh
Spelregelboekje | Must |  |  | Eerste versie van de spelregels, hoeft niet perfect te zijn maar wel duidelijk. | Todd
User Testing | Must |  |  | Doel van deze sprint is het spel speelbaar maken en meerdere keren spelen om een feeling te krijgen voor de balancing. | Allen

## Sprint 2 Backlog
Onderdeel | Moscow | Prioriteit | Status | User Story | Assignees | Points | Name | Points wk 1 | Points wk 2
Bord Foundation | Must |  |  | De basis van het bord is compleet, het bord kan uit elkaar gehaald worden om het makkelijk op te bergen. Op de foundation kan het design gemaakt worden. | Alexander, Todd | 30 | Avesh | 10 | x
Obstakels concept | Must |  |  | Er zijn minimaal 3 verschillende obstakels, met duidelijk verschil in functionaliteit. | Sebastian | 2 | Sebastian | 12 | 10
Obstakels Productie | Must |  | printklaar | Er zijn speelstukken voor elke soort obstakels. | Sebastian | 10 | Michael | 10 | 10
Geld Fiches | Must |  |  | Er zijn fiches die het geld representeren. De waardes op de fiches zijn 1, 2 en 5. | Ariano | 5 | Ariano | 10 | 10
Graan Fiches | Must |  |  | Er zijn fiches die het graan representeren. De waardes op de fiches zijn 1 of 5. | Ariano | 5 | Todd | 10 | 10
Kaarten Design | Must |  |  | Er zijn kaarten met gebeurtenissen die er mooi uit zien en passen bij het thema. De tekst moet duidelijk zijn. | Todd | 5 | Alexander | 10 | 10
Bord Design | Must |  |  | Er zijn minimaal 3 verschillende designs die op de foundation gebaseerd zijn. | Michael & Avesh | 20
Bord Design Productie | Must |  |  | Het gekozen design op de foundation produceren. | Iedereen wk 2 | 45
Vertaling oud Engels | Must |  |  | De kaarten en handleiding moeten in het Oud Engels (18/19e eeuw) | Alexander | 3
30 verschillende events | Must |  |  | Lichtere gebeurtenissen toevoegen zodat de dynamiek niet veel geschaafd hoeft te worden. | Todd | 2
Pionnen | Could |  |  | Thematische speelstukken |  | 5
Boten | Should |  | printklaar | Thematische speelstukken | Sebastian | 5
User Testing | Must
137

## P2 Sprint 1
Onderdeel | Prioriteit | User story | Story points
digital dices |  | As a user, I want to be able to roll two dices in the digital component, because I won't need physical dices if I can. | 1
digital dices |  | As a user, I want to see a 3D animation when I roll the dices, because the current animation is boring. | 16
gebeurtenissen |  | As a user, I want to be able to draw an event card, such that there is a fancy animation displayed when I do, because I don't want to shuffle the cards every time. | 4
gebeurtenissen |  | As a user, I want to be able to draw an event card, such that the in game events are displayed, because otherwise the feature is useless. | 1
gebeurtenissen |  | As a user, I want the program to store a persistent list of events and to read them into the program when I start a game, because I'm too lazy to re-enter the events whenever I want to play a game. | 8
gebeurtenissen |  | As a user, I want the program to execute the effect of the drawn event, because it saves me effort and it prevents cheating. | 16
fiches |  | As a user, I want the program to store the amount of dollars and wheat that are in my posession, so I don't have to mess around with fiches. | 1
boot |  | As a user, I want the program to know whether I have a boat or not, and how many wheat is loaded on my boat, because it supports future features and saves me effort. | 1
spelers invoeren |  | As a user, I want to be able to enter the names of 2-4 players before I start a game, so I have a personalized experience and it's easier to remember who's at turn. | 2
beurt info |  | As a user, I want the program to display a screen that shows which player is on turn and statistics about the player, because I need information from the game to make good decisions. | 2
game control |  | As a user, I want the program to be able to execute a series of turns until the game is over, because it supports the other things I want and makes the digital component more easy to use. | 4
overzicht |  | As a user, I want the program to display the names and data of all players in a corner on the turn screen, because it gives me extra information that I can base my decisions on and that information is otherwise ommitted by the use of the digital component. | 2
GUI |  | As a user, I want the GUI to switch to the proper screens automatically, because not everything fits into a single screen. | 8
GUI |  | As a user, I want the GUI to communicate my actions to the back-end code, because I want the program to remember the state of the game. | 8
GUI |  | As a user, I want to be able to play the game without physical dices or event cards, because I want a working and usable digital component. | NVT
bugfixes |  | As a user, I want the known bugs to be resolved, because bugs in the program frustrate my experience. | 15
Testing |  | As a developer, I want the program to have unit tests, so I can identify bugs in at an early stage. | 40
18.4286
|  |  | 129 |  | 129
|  |  | 129 | 0 | 110.5714
|  |  | 129 | 0 | 92.1429
|  |  | 129 | 0 | 73.7143
|  |  | 129 | 0 | 55.2857
|  |  | 129 | 0 | 36.8571
|  |  | 129 | 0 | 18.4286
|  |  | 27 | 102 | -7.1054e-15

## P2 Sprint 2
Onderdeel | Prioriteit | User story | Story points
Thema |  | As a user, I want the user interface to have an interesting theme that is consistent in all scenes so I am appealed to use the digital component. | 3
Path tracking |  | As a user, I want the program to remember where I am on the board, so my user experience can be improved by a smarter GUI. | 20
Rule checking |  | As a user, I want the program to know the rules of the game and apply them, so I don't overlook rules and cheating is prevented. | 4
Event automation |  | As a user, I want the program to execute the effect of the drawn event, because it saves me effort and it prevents cheating. | 8
Settings |  | As a user, I want to be able to change the settings of the game, so I can personalize my user experience and disable certain functions. | 5
Victory |  | As a user, I want to see a celebration animation when I win the game, because winning is exciting. | 7
Victory |  | As a user, I want to see a brief summary of the game when I win, so I can see the stats. | 1
Event customization |  | As a user, I want to be able to create my own set of events, so I can play with my own set of events. | 6
Unit testing |  | As a developer, I want the program to have unit tests, so I can easily identify bugs. | 8
User testing |  | As a developer, I want the program to be tested by users, so I can identify overlooked bugs and get feedback on the program. | 2
Digital dices |  | As a user, I want to see a 3D animation when I roll the dices, because the current animation is boring. | 16
64
2.2857
|  |  | 64 | 3 | 64
|  |  | 64 | 0 | 61.7143
|  |  | 64 | 0 | 59.4286
|  |  | 64 | 0 | 57.1429
|  |  | 64 | 0 | 54.8571
|  |  | 64 | 0 | 52.5714
|  |  | 64 | 0 | 50.2857
|  |  | 64 | 0 | 48
|  |  | 46 | 18 | 45.7143
|  |  | 46 | 0 | 43.4286
|  |  | 36 | 10 | 41.1429
|  |  | 36 | 0 | 38.8571
|  |  | 36 | 0 | 36.5714
|  |  | 36 | 0 | 34.2857
|  |  | 36 | 0 | 32
|  |  | 29 | 7 | 29.7143
|  |  | 24 | 5 | 27.4286
|  |  | 24 | 0 | 25.1429
|  |  | 24 | 0 | 22.8571
|  |  | 17 | 7 | 20.5714
|  |  | 17 | 0 | 18.2857
|  |  | 17 | 0 | 16
|  |  | 17 | 0 | 13.7143
|  |  | 17 | 0 | 11.4286
|  |  | 17 | 0 | 9.1429
|  |  | 17 | 0 | 6.8571
|  |  | 0 | 17 | 4.5714
|  |  | 0 |  | 2.2857
|  |  | 0 | 0 | 2.4869e-14